## Slide 1
BLUE PRINT CONSTRUCTS
TAMU Harrington Lab 303 — Proposal package
Solicitation: 2025-06813
Blue Print Constructs (legal: RK Residential Homes and Commercial Constructions, LLC)
Submission date __________ · Document prepared 2026-05-23

## Slide 2
About Blue Print Constructs
Blue Print Constructs — legal entity RK Residential Homes and Commercial Constructions, LLC; founded 2022, Texas-incorporated, founder-led.
NAICS: primary 236220 (Commercial & Institutional Building Construction); 13 codes registered.
Federal IDs: UEI LM4YHVQ71QG7 · CAGE 9LET0 · SAM.gov status: active.
Set-aside posture: Texas HUB, DFW MSDC MBE, Small Business, Minority-owned
Self-perform trades: Interior and exterior painting, Drywall and sheetrock — install, tape, bed, texture, Tile setting, Flooring — laminate, vinyl, LVT, tile, hardwood refinish, Trims and baseboards / crown molding / interior carpentry, Roofing (composition, flat, metal — repairs and replacement).
Blue Print Constructs · tamu-harrington-2025-06813
Slide 2

## Slide 3
Project understanding
`RK Residential Homes and Commercial Constructions, LLC dba Blue Print Constructs` is pleased to submit this Competitive Sealed Proposal for the renovation of the **Harrington Education Center Lab 303** (Texas A&M University, Bldg 0435, College Station, TX). We acknowledge the N…
(See full proposal for additional detail.)
(See full proposal for additional detail.)
Blue Print Constructs · tamu-harrington-2025-06813
Slide 3

## Slide 4
Technical approach
A. Project understanding: The Harrington Education Center Lab 303 Renovation is a **single-room renovation of an active educational laboratory space** at **540 Ross Street, Harrington Tower (Bldg #0435)** on TAMU's College St…
B. Phased work plan (60–90 calendar days, single-shift baseline): - Notice to Proceed + contract execution (per SSC UGSC Section 00 72 00) - Pre-construction meeting with SSC PM (Joelle Shidemantle, `Joelle.Shidemantle@sscserv.com`, (979)…
C. Lab-specific considerations (the pain-points worth pricing for): This is the differentiator. Most GCs treat single-room labs like classroom finish work and then get burned on the lab utilities. We don't.
D. Coordination with the academic calendar: The CSP package leaves Project Start and Substantial Completion as "TBD" — proposers select their own Substantial Completion duration in CSP Part 1 (Section 00 42 13), and this is scored at 10% o…
E. Long-lead items + procurement plan: | Item | Typical lead time | Order placement target | Risk if missed | |---|---|---|---| | Lab casework (per A2.1/A2.2 + H2I Sub-06 specifics) | 8–10 weeks fabricated; 10–12 weeks with custom configu…
F. Assumptions + clarifications: We submit this proposal subject to the following assumptions. If any prove false at the pre-construction meeting or during construction, the resulting scope adjustment will be handled per the change-…
Blue Print Constructs · tamu-harrington-2025-06813
Slide 4

## Slide 5
Project team
Role | Named lead
Project Executive | ____________________
Project Manager (PM of Record) | ____________________
Project Superintendent | ____________________
Safety Lead | ____________________
Project Estimator | ____________________
Blue Print Constructs · tamu-harrington-2025-06813
Slide 5

## Slide 6
Past performance — Project 1 of 3
Hindu Temple of Southlake — Place of Religious Worship renovation
Owner: North Texas Hindu Heritage Society
Contract value: —
Completion: —
Role: GC · Delivery: Negotiated lump-sum (owner direct)
Scope summary
≈10,700 SF Assembly A-3 (Place of Religious Worship) renovation including demolition, finishes, toilet partitions (phenolic), and partition framework. Drawings on file dated 2025-06-20 (PDF), 2025-09-12 (Arch + Structural updates).
Blue Print Constructs · tamu-harrington-2025-06813
Slide 6

## Slide 7
Past performance — Project 2 of 3
Holiday Inn (Hall Park) — hospitality renovation
Owner: Holiday Inn franchisee at Hall Park, Frisco, TX
Contract value: —
Completion: —
Role: GC · Delivery: —
Scope summary
Commercial renovation projects for hospitality client per Rocky Nudurupati's professional profile.
Blue Print Constructs · tamu-harrington-2025-06813
Slide 7

## Slide 8
Past performance — Project 3 of 3
250-500+ single-family-home portfolio (cumulative; multiple owners)
Owner: Multiple — primarily through GC partners That 1 Painter, Touchmark, Bridge View Build, Hill Design Build
Contract value: —
Completion: Ongoing 2022–present
Role: Specialty trade subcontractor · Delivery: —
Scope summary
Interior + exterior painting, drywall, flooring, tile, trims, baseboards, roofing repairs across 250+ (per BPC info) to 500+ (per BPC Profile) single-family homes since 2022. Primarily executed as a specialty sub for the four featured GC clients.
Blue Print Constructs · tamu-harrington-2025-06813
Slide 8

## Slide 9
Schedule milestones
Milestone | Date / duration
Calendar-day axis from Day 1 (NTP) to Day 100 (final comple… | —
One swimlane per trade | —
Critical path highlighted (casework + fume-hood-if-scope) | —
Phase boundaries at Day 14, Day 25, Day 45, Day 70, Day 100 | —
Long-lead procurement bars (typically off-site, shown as se… | —
EHS shutdown windows shown as red event markers | —
Blue Print Constructs · tamu-harrington-2025-06813
Slide 9

## Slide 10
Quality & safety
QC: > **Page target:** 1–2 pages when typeset. > **Approach:** Three-phase inspection (prep / in-progress / completion) per the US Army Corps of Engineers "3-phase QC" pattern that TAMU System UGSC has historically required. Article refere…
Safety: Our firm operates under a documented Injury and Illness Prevention Program. We hold a daily pre-task safety briefing on every active site; every employee and subcontractor on site has stop-work authority for any hazard they observe…
(Additional QC / safety detail in the full proposal.)
(Additional QC / safety detail in the full proposal.)
Blue Print Constructs · tamu-harrington-2025-06813
Slide 10

## Slide 11
Price proposal summary
TOTAL PROPOSED PRICE
$____________________
**STATUS: FORMULAS REFINED 2026-05-23 against the actual downloaded CSP package** (drawings A0.1–E1.2 + Project Manual). Quantities still `______________` after Bluebeam takeoff against A2.1 / P1.1 / M1.1 / E1.2. > Cross-references: `../pr…
(See full proposal for itemized pricing detail.)
(See full proposal for itemized pricing detail.)
Blue Print Constructs · tamu-harrington-2025-06813
Slide 11

## Slide 12
Why Blue Print Constructs
Texas-based small business — self-perform across 8 core trades.
Diverse-business posture: TX HUB, DFW MSDC MBE, Small Business, Minority-owned.
Sector breadth: Residential, Commercial, Industrial, Institutional.
Founder-led PMP / CSM operator with 22 years delivery leadership — Ravikiran (Rocky) Nudurupati.
Blue Print Constructs · tamu-harrington-2025-06813
Slide 12

## Slide 13
Q & A
THANK YOU FOR YOUR CONSIDERATION
Ravikiran (Rocky) Nudurupati
Founder & Managing Director / Owner (100%)
rocky@blueprintconstructs.com
(469) 213-1838
https://www.blueprintconstructs.com
Bid tamu-harrington-2025-06813 · 2026-05-23