## Slide 1
TAMU Harrington Lab 303 — Proposal package
Solicitation: 2025-06813
Blue Print Constructs (legal: RK Residential Homes and Commercial Constructions, LLC) — Submission Date TBD by reviewer
Prepared 2026-05-23

## Slide 2
About Blue Print Constructs
Legal name: RK Residential Homes and Commercial Constructions, LLC dba Blue Print Constructs
NAICS: primary 236220 (Commercial & Institutional Building Construction); 13 codes registered total
UEI: LM4YHVQ71QG7 CAGE: 9LET0 SAM.gov status: active
Set-aside posture: small business, minority-owned, MBE (DFW MSDC certified), TX HUB (Certified (Texas Comptroller HUB Program via DFW MSDC affiliate))
Self-perform trades: Interior and exterior painting, Drywall and sheetrock — install, tape, bed, texture, Tile setting, Flooring — laminate, vinyl, LVT, tile, hardwood refinish, Trims and baseboards / crown molding / interior carpentry, Roofing (composition, flat, metal — repairs and replacement)
tamu-harrington-2025-06813
Slide 2

## Slide 3
Project understanding
Selective interior demolition of existing finishes, casework, and ceiling
New finishes (LVT and/or chemical-resistant sheet vinyl flooring, 4" rubber base, painted GWB walls, suspended acoustical ceiling)
Lab-grade casework with phenolic-resin or epoxy-resin work surfaces
tamu-harrington-2025-06813
Slide 3

## Slide 4
Technical approach
A. Project understanding: The Harrington Education Center Lab 303 Renovation is a **single-room renovation of an active educational laboratory space** at **540 Ross Street, Harrington Tower (Bldg #0435)** on TAMU's College St…
B. Phased work plan (60–90 calendar days, single-shift baseline): - Notice to Proceed + contract execution (per SSC UGSC Section 00 72 00) - Pre-construction meeting with SSC PM (Joelle Shidemantle, `Joelle.Shidemantle@sscserv.com`, (979)…
C. Lab-specific considerations (the pain-points worth pricing for): This is the differentiator. Most GCs treat single-room labs like classroom finish work and then get burned on the lab utilities. We don't.
D. Coordination with the academic calendar: The CSP package leaves Project Start and Substantial Completion as "TBD" — proposers select their own Substantial Completion duration in CSP Part 1 (Section 00 42 13), and this is scored at 10% o…
E. Long-lead items + procurement plan: | Item | Typical lead time | Order placement target | Risk if missed | |---|---|---|---| | Lab casework (per A2.1/A2.2 + H2I Sub-06 specifics) | 8–10 weeks fabricated; 10–12 weeks with custom configu…
F. Assumptions + clarifications: We submit this proposal subject to the following assumptions. If any prove false at the pre-construction meeting or during construction, the resulting scope adjustment will be handled per the change-…
tamu-harrington-2025-06813
Slide 4

## Slide 5
Project team
Role | Name
I. Resume + reference exhibits | [USER TO FILL — name]
tamu-harrington-2025-06813
Slide 5

## Slide 6
Past performance
Project | Owner | Value | Completion | Scope summary
Hindu Temple of Southlake |  |  |  | **Hindu Temple of Southlake** — North Texas Hindu Heritage Society (nonprofit religious owner); ≈10,700 SF Assembly A-3 (Place of Religious Worship) renovation at 595 South Kimball Avenue, Southlake, TX 76092; owner-sid…
Holiday Inn (Hall Park) |  |  |  | **Holiday Inn (Hall Park, Frisco)** — Holiday Inn franchisee (hospitality owner); commercial renovation at Hall Park, Frisco, TX; role: GC. Contract value, scope detail, and completion date: [USER TO FILL — cited by nam…
250-500+ single-family-home portfolio |  |  |  | **250–500+ single-family-home portfolio (cumulative since 2022)** — executed primarily as a specialty trade sub through GC partners That 1 Painter, Touchmark, Bridge View Build, and Hill Design Build across the DFW metr…
tamu-harrington-2025-06813
Slide 6

## Slide 7
Schedule
Calendar-day axis from Day 1 (NTP) to Day 100 (final completion)
One swimlane per trade
Critical path highlighted (casework + fume-hood-if-scope)
Phase boundaries at Day 14, Day 25, Day 45, Day 70, Day 100
Long-lead procurement bars (typically off-site, shown as separate row)
EHS shutdown windows shown as red event markers
Owner-decision points (submittal approval, RFI responses, lab equipment delivery if OFCI) shown as diamond markers
Substantial completion and final completion shown as flag markers
tamu-harrington-2025-06813
Slide 7

## Slide 8
Quality & safety
QC: > **Page target:** 1–2 pages when typeset. > **Approach:** Three-phase inspection (prep / in-progress / completion) per the US Army Corps of Engineers "3-phase QC" pattern that TAMU System UGSC has historically required. Article refere…
Safety: Our firm operates under a documented Injury and Illness Prevention Program. We hold a daily pre-task safety briefing on every active site; every employee and subcontractor on site has stop-work authority for any hazard they observe…
tamu-harrington-2025-06813
Slide 8

## Slide 9
Price proposal
**STATUS: FORMULAS REFINED 2026-05-23 against the actual downloaded CSP package** (drawings A0.1–E1.2 + Project Manual). Quantities still `[USER TO FILL]` after Bluebeam takeoff against A2.1 / P1.1 / M1.1 / E1.2. > Cross-references: `../price-references.md` f…
tamu-harrington-2025-06813
Slide 9

## Slide 10
Submission checklist status
Ready: 0 item(s)
Partial: 0 item(s)
Pending: 24 item(s)
tamu-harrington-2025-06813
Slide 10

## Slide 11
Why Blue Print Constructs
Texas-based small business — self-perform across 8 core trades
Diverse-business posture: TX HUB, MBE (DFW MSDC certified), small business, minority-owned
Sector breadth: Residential, Commercial, Industrial, Institutional
Founder-led PMP / CSM operator with 22 years delivery leadership — Ravikiran (Rocky) Nudurupati
tamu-harrington-2025-06813
Slide 11

## Slide 12
Q&A / Next steps
Ravikiran (Rocky) Nudurupati — Founder & Managing Director / Owner (100%)
Email: rocky@blueprintconstructs.com
Phone: (469) 213-1838
Web: https://www.blueprintconstructs.com
Next steps: site walk, RFI consolidation, sub bid coordination, final pricing.
tamu-harrington-2025-06813
Slide 12